## Cover
Gap Analysis & Remediation
Assessment register · entanglement lens · per scope (GLB / DE / IT)
Client | Meridian Elevator Group
Engagement | Carve-out & separation discovery
Prepared by | Noema · Niya Consulting
Status | Sample — illustrative engagement data
Version / date | v1.0 · June 2026
Classification | Confidential — for discussion purposes
Contents
1. Summary | Counts by type and severity, remediation effort
2. Gap Register | Full register — every gap traces to a discovery item
Every line in this workbook traces to a discovery item, an interview moment, or a documented source. Sample data only — no client confidential content.

## Gap Register
Gap register — entanglement lens
Every gap traces to a discovery item and its interview moment
Gap ID | Process ref | Scope | Finding | Type | Severity | Remediation | Effort (days) | Owner | Status | Wave
GAP-001 | P2P-L2-20 | GLB | Pricing reads from parent's shared price master; feed terminates at separation | Integration | High | Build standalone price master; one-time migration + dual-run 4 weeks | 18 | A. Vogel | In remediation design | Phase 1
GAP-002 | P2P-L2-70 | IT | SdI e-invoices manually rekeyed daily; parent system rejects local VAT codes | Integration | High | Native SdI channel + own VAT determination | 24 | A. Vogel | Open | Phase 1
GAP-003 | P2P-L2-40 | GLB | Approvals above €50k via email; no audit trail | Config | High | Value-threshold approval workflow with full audit trail | 8 | J. Weiss | Open | Phase 1
GAP-004 | P2P-L2-40 | DE | Works-council sign-off on signed PDF, off-system | Config | Medium | Statutory hold step in workflow | 4 | H. Brandt | Open | Phase 2
GAP-005 | P2P-L2-80 | GLB | 3-way match performed inside parent AP service centre | Process | High | Stand-alone payables matching; TSA bridge 9 months | 16 | J. Weiss | TSA agreed | Phase 1
GAP-006 | P2P-L2-90 | GLB | All payment runs via parent treasury | Integration | High | Own treasury workbench + bank connectivity | 22 | K. Maurer | In remediation design | Phase 1
GAP-007 | O2C-L2-20 | GLB | Credit decisions depend on parent bureau feed | Integration | High | Own credit policy + external bureau contract | 12 | L. Conti | Open | Phase 1
GAP-008 | O2C-L2-50 | IT | Billing SdI handling manual at month-end peak | Integration | Medium | Covered by GAP-002 channel; billing config | 6 | A. Vogel | Open | Phase 2
GAP-009 | O2C-L2-60 | GLB | Collections run on spreadsheets; no dunning | Config | Medium | Collections workbench, 3-step dunning | 6 | L. Conti | Open | Phase 2
GAP-010 | R2R-L1-031 | GLB | Close executed in parent consolidation platform | Process | High | Own ledger + group reporting pack; TSA 12 months | 30 | K. Maurer | TSA agreed | Phase 1
GAP-011 | R2R-L1-032 | GLB | Intercompany with parent becomes third-party trade | Process | High | Trading terms, master data, tax review | 14 | K. Maurer | In remediation design | Phase 1
GAP-012 | H2R-L1-051 | DE·IT | Payroll runs in parent HCM | Process | High | Local payroll providers; parallel run 2 cycles | 20 | HR advisor | TSA agreed | Phase 2
GAP-013 | P2P-L2-60 | IT | Goods receipt on paper protocol at IT plant | Process | Low | Mobile GR + statutory register | 5 | M. Rossi | Open | Phase 3
GAP-014 | P2P-L2-10 | DE | Paper requisition pad on shop floor (habit) | Process | Low | Fold into self-service core; change mgmt | 2 | H. Brandt | Open | Phase 3
GAP-015 | IT-Run | GLB | 60+ applications hosted in parent estate | Integration | High | App-by-app disposition (rehost / replace / retire) | 45 | A. Vogel | In remediation design | Phase 1–3

## Summary
Summary
Counts reference the register — recalculated live in Excel
By severity | High | Medium | Low | Total
Gaps | 9 | 3 | 2 | 15
By type | Integration | Config | Process
Gaps | 6 | 3 | 6
Effort | Days (sum)
Remediation effort | 232