## Cover
Process Flows L0–L4
As-is and target process taxonomy · multi-site (Global / DE / IT)
Client | Meridian Elevator Group
Engagement | Carve-out & separation discovery
Prepared by | Noema · Niya Consulting
Status | Sample — illustrative engagement data
Version / date | v1.0 · June 2026
Classification | Confidential — for discussion purposes
Contents
1. L0 Landscape | Enterprise process landscape — 8 mega-processes
2. L1 Breakdown | Process groups per L0, with disposition
3. L2 Procure-to-Pay | Step level — as-is vs target, fit and confidence
4. L2 Order-to-Cash | Step level — as-is vs target, fit and confidence
5. L3 Detail | Activity level for critical L2 steps
6. L4 Sample | Task level — SdI e-invoice handling (IT)
7. Site Variants | Variant register with statutory basis
Every line in this workbook traces to a discovery item, an interview moment, or a documented source. Sample data only — no client confidential content.

## L0 Landscape
L0 · Enterprise process landscape
Meridian Elevator Group · separation perimeter · sample data
L0 ID | Mega-process | Process owner | Primary as-is system(s) | Sites in scope | # L1 | Separation exposure | Status
L0-01 | Procure-to-Pay | CPO · K. Maurer (interim) | Legacy ERP + parent AP service centre | GLB · DE · IT | 6 | High | Baselined
L0-02 | Order-to-Cash | Sales ops · L. Conti | Legacy ERP + parent credit bureau feed | GLB · DE · IT | 7 | High | Baselined
L0-03 | Record-to-Report | CFO · K. Maurer | Parent consolidation platform | GLB | 5 | High | Baselined
L0-04 | Plan-to-Produce | Plant managers · DE/IT | Site MES + legacy ERP | DE · IT | 6 | Medium | Baselined
L0-05 | Hire-to-Retire | HR · external advisor | Parent HCM suite | GLB · DE · IT | 4 | High | In assessment
L0-06 | Acquire-to-Dispose (assets) | Finance · J. Weiss | Legacy ERP fixed assets | GLB | 3 | Low | Baselined
L0-07 | Service-to-Cash (field) | Service ops · P. Lang | Field tool + parent billing | DE · IT | 5 | Medium | In assessment
L0-08 | IT-Run (application estate) | IT · A. Vogel | Parent-hosted estate, 60+ apps | GLB | 4 | High | Baselined

## L1 Breakdown
L1 · Process groups
Disposition per group · sever / replace / keep / TSA
L0 | L1 ID | Process group | Scope | As-is system | Entangled with parent | Disposition | Target
P2P | L1-011 | Source & contract | GLB | Parent sourcing suite | Yes | Sever — TSA 6m | Target · Sourcing
P2P | L1-012 | Requisition to order | GLB·DE·IT | Legacy ERP | No | Replace | Target · Self-Service Procurement
P2P | L1-013 | Price & catalogue management | GLB | Parent shared price master | Yes | Sever — day one | Own price master
P2P | L1-014 | Goods receipt & returns | DE·IT | Legacy ERP / paper | No | Replace | Target · Inventory
P2P | L1-015 | Invoice to pay | GLB·IT | Parent AP service centre | Yes | Sever — TSA 9m | Own Payables + SdI integration
P2P | L1-016 | Supplier master | GLB | Parent MDM | Yes | Sever — day one | Own MDM (slim)
O2C | L1-021 | Customer & credit master | GLB | Parent credit bureau feed | Yes | Sever — TSA 3m | Own credit policy
O2C | L1-022 | Quote to order | GLB·DE·IT | Legacy CRM + ERP | No | Replace | Target · Order Management
O2C | L1-023 | Fulfil & ship | DE·IT | Legacy ERP + WMS | No | Keep, integrate | Keep WMS · new interfaces
O2C | L1-024 | Bill to cash | GLB·IT | Legacy ERP + SdI workaround | Partial | Replace | Target · Billing + SdI native
O2C | L1-025 | Disputes & collections | GLB | Email + spreadsheets | No | Replace | Target · Collections workbench
R2R | L1-031 | General ledger & close | GLB | Parent consolidation platform | Yes | Sever — TSA 12m | Own ledger, group reporting
R2R | L1-032 | Intercompany (to parent) | GLB | Parent netting centre | Yes | Redesign | Third-party trading terms
R2R | L1-033 | Treasury & payments | GLB | Parent treasury | Yes | Sever — day one | Own treasury workbench
PTP | L1-041 | Production scheduling | DE·IT | Site MES | No | Keep | Keep · integrate
PTP | L1-042 | Quality management | DE·IT | Site QMS + binders | No | Replace | Target · Quality
H2R | L1-051 | Payroll | DE·IT | Parent HCM | Yes | Sever — TSA 12m | Local payroll providers
H2R | L1-052 | Time & attendance | DE·IT | Site clocks + parent HCM | Partial | Replace | Target · Workforce

## L2 Procure-to-Pay
L2 · Procure-to-Pay — step level
As-is (entangled) vs target (stand-alone) · confidence per assessment
Step | L2 ID | As-is | As-is system | Pain / workaround | Entangled | Target | Fit | Confidence | Site variants
10 | P2P-L2-10 | Demand raised | Email / verbal | Untracked demand | No | Self-service requisition | Gap · Config | High | —
20 | P2P-L2-20 | Price lookup | Parent shared price master | Manual export to Excel weekly | Yes | Standalone price master | Gap · Config | High | —
30 | P2P-L2-30 | Create requisition | Legacy · Procurement | — | No | Self-service requisition | Fit | High | —
40 | P2P-L2-40 | Approvals | Teams / email chase | No audit trail above €50k | No | Automated value-threshold routing | Gap · Config | High | DE: works-council review
50 | P2P-L2-50 | Convert to PO | Legacy · Purchase Orders | — | No | Touchless PO ≤ €50k | Fit | Medium | —
60 | P2P-L2-60 | Goods receipt | Legacy ERP + paper | Paper notes at IT plant | No | Mobile GR | Gap · Config | Medium | IT: paper protocol register
70 | P2P-L2-70 | Invoice capture | Parent AP service centre | SdI invoices rekeyed daily (2 FTE) | Yes | Own capture + SdI native | Gap · Integration | Needs-verify | IT: SdI / FatturaPA statutory
80 | P2P-L2-80 | 3-way match | Parent AP service centre | — | Yes | Automated 3-way match | Gap · Config | Medium | —
90 | P2P-L2-90 | Payment run | Parent treasury | — | Yes | Own treasury workbench | Gap · Integration | Medium | —

## L2 Order-to-Cash
L2 · Order-to-Cash — step level
As-is vs target · sample subset
Step | L2 ID | As-is | As-is system | Pain / workaround | Entangled | Target | Fit | Confidence | Site variants
10 | O2C-L2-10 | Quote | Legacy CRM | Re-keyed into ERP | No | Integrated quote-to-order | Gap · Config | High | —
20 | O2C-L2-20 | Credit check | Parent credit bureau feed | Feed dies at separation | Yes | Own credit policy + scoring | Gap · Integration | Needs-verify | —
30 | O2C-L2-30 | Order entry | Legacy ERP | — | No | Order management | Fit | High | —
40 | O2C-L2-40 | Fulfil & ship | Legacy ERP + WMS | — | No | Keep WMS, new interfaces | Fit | Medium | —
50 | O2C-L2-50 | Billing | Legacy ERP + SdI workaround | Manual SdI handling (IT) | Partial | Billing + SdI native | Gap · Integration | Medium | IT: SdI statutory
60 | O2C-L2-60 | Collections | Email + spreadsheets | No dunning discipline | No | Collections workbench | Gap · Config | High | —

## L3 Detail
L3 · Activity detail — critical steps
P2P-L2-40 Approvals · P2P-L2-70 Invoice capture
L2 ref | L3 ID | Activity | Actor (as-is) | As-is mechanics | Target mechanics | R | A | C | I
P2P-L2-40 | L3-401 | Determine approval path | Requester | Asks around / forwards email | System derives path from value + category | Requester | Line mgr | Finance | —
P2P-L2-40 | L3-402 | Approve ≤ €50k | Line manager | Email reply, often delayed | One-tap approval, mobile | Line mgr | Line mgr | — | Requester
P2P-L2-40 | L3-403 | Approve > €50k | Category head + Finance | Email chain, no audit trail | Sequential workflow, full audit trail | Category head | CFO | Finance | Requester
P2P-L2-40 | L3-404 | DE works-council review | Works council (DE) | Signed PDF, off-system | Workflow step with statutory hold | WC delegate | Plant mgr DE | HR | Requester
P2P-L2-70 | L3-701 | Receive SdI e-invoice | AP clerk (IT) | Portal download, manual | Native SdI channel | System | AP lead | — | —
P2P-L2-70 | L3-702 | Validate VAT codes | AP clerk (IT) | Manual rekey — parent system rejects local codes | Automatic validation against own master | System | AP lead | Tax | —
P2P-L2-70 | L3-703 | Register protocol number | AP clerk (IT) | Local register, off-system | System-generated, statutory format | System | AP lead | — | Auditor
P2P-L2-70 | L3-704 | Route exceptions | AP clerk | Email to buyer | Exception workbench with SLA | AP clerk | AP lead | Buyer | —

## L4 Sample
L4 · Task level — SdI e-invoice handling (Italy)
Keystroke-level decomposition of L3-702 · the daily 2-FTE workaround
L3 ref | L4 ID | Task | Actor | System / screen | Duration (as-is) | Target | Eliminated?
L3-702 | L4-7021 | Open SdI portal, download XML batch | AP clerk | SdI portal · browser | 10 min/day | Automatic pull, native channel | Yes
L3-702 | L4-7022 | Open each XML, read VAT code | AP clerk | XML viewer | 45 min/day | Parsed automatically | Yes
L3-702 | L4-7023 | Map VAT code to parent code table | AP clerk | Excel mapping sheet v23 | 60 min/day | Own VAT determination | Yes
L3-702 | L4-7024 | Rekey invoice into parent AP | AP clerk | Parent AP · invoice entry | 120 min/day | No rekeying — direct post | Yes
L3-702 | L4-7025 | Note protocol number in register | AP clerk | Local register (paper) | 20 min/day | System-generated | Yes
L3-702 | L4-7026 | Reconcile rejects with buyer | AP clerk | Email | 30 min/day | Exception workbench | Reduced

## Site Variants
Site variant register
Variants survive only with a documented basis — habits fold into the core
Variant ID | Site | Process ref | Variant | Basis | Classification | Disposition | Evidence (interview)
V-01 | IT | P2P-L2-70 | SdI / FatturaPA e-invoicing | Legge 205/2017 — statutory | Justified variant | Build native integration | M. Rossi · 14:31
V-02 | IT | P2P-L2-60 | Protocol register | DPR 600/1973 — statutory | Justified variant | System-generated register | M. Rossi · 14:38
V-03 | DE | P2P-L2-40 | Works-council review on tooling change | BetrVG §87 — statutory | Justified variant | Workflow step with hold | H. Brandt · 09:55
V-04 | IT | O2C-L2-50 | Bollo stamp duty on invoices | Statutory | Justified variant | Config in billing | L. Conti · 11:20
V-05 | DE | P2P-L2-10 | Paper requisition pad on shop floor | Habit — predates 2014 system | To harmonize | Fold into self-service core | H. Brandt · 10:12
V-06 | IT | P2P-L2-40 | Verbal approval for plant consumables | Habit | To harmonize | Fold into value-threshold core | M. Rossi · 14:50