## Cover
Noema Workbook — Master
Single source of the discovery record · locked baseline v1.0
Client | Meridian Elevator Group
Engagement | Carve-out & separation discovery
Prepared by | Noema · Niya Consulting
Status | Sample — illustrative engagement data
Version / date | v1.0 · June 2026
Classification | Confidential — for discussion purposes
Contents
1. Context | Engagement brief and scope, as locked
2. Stakeholders | Roster with interview ownership
3. Interviews | Track register with extraction counts
4. Discovery Items | The spine — every finding, classified, dispositioned
5. Open Points | Decisions register — who must decide, by when
6. Decision Log | Resolved decisions with rationale
7. Traceability | Deliverable line → item → interview moment
Every line in this workbook traces to a discovery item, an interview moment, or a documented source. Sample data only — no client confidential content.

## Context
Engagement context — as locked
Synthesis lock 2026-06-05 · baseline v1.0
Field | Value
Client | Meridian Elevator Group
Situation | Carve-out from parent conglomerate; stand-alone by day one
Perimeter | 3 sites — DE plant, IT plant, global SSC · 8 mega-processes
Systems posture | Legacy ERP (keep short-term) + parent estate (sever) → target platform selection follows
Lens | Entanglement — every parent dependency must surface, with a severance disposition
Engagement window | 34–42 consulting days · 2026-04-14 to 2026-06-05
Baseline | Locked 2026-06-05 · 14:02 · by K. Maurer (CFO) and engagement principal

## Stakeholders
Stakeholder roster
Owner = who conducts the interview · every delegated item still reaches a disposition
# | Name | Role | Site | Influence | Interest | Interview owner | Duration | Status
1 | K. Maurer | CFO | GLB | High | High | Principal-led | 90 min | Done
2 | H. Brandt | Plant manager | DE | High | Medium | Principal-led | 60 min | Done
3 | S. Keller | SSC lead | GLB | High | High | Principal-led | 60 min | Done
4 | M. Rossi | Plant ops | IT | Medium | High | Platform-conducted | 45 min | Done
5 | J. Weiss | AP team lead | GLB | Medium | Medium | Platform-conducted | 30 min | Done
6 | L. Conti | Order desk | IT | Medium | Medium | Platform-conducted | 30 min | Done
7 | A. Vogel | IT applications | GLB | High | Medium | Platform-conducted | 45 min | Done
8 | P. Lang | Logistics | DE | Low | Medium | Platform-conducted | 30 min | Done

## Interviews
Interview register
Items extracted live · accepted / reclassified / rejected by the consultant
Track | Stakeholder | Owner | Date | Items extracted | Accepted | Reclassified | Rejected | Coverage
INT-01 | K. Maurer | Principal | 2026-04-22 | 19 | 16 | 2 | 1 | 100%
INT-02 | H. Brandt | Principal | 2026-04-24 | 14 | 12 | 1 | 1 | 100%
INT-03 | S. Keller | Principal | 2026-04-25 | 22 | 19 | 3 | 0 | 100%
INT-04 | M. Rossi | Platform | 2026-04-28 | 13 | 11 | 2 | 0 | 100%
INT-05 | J. Weiss | Platform | 2026-04-28 | 9 | 8 | 0 | 1 | 92%
INT-06 | L. Conti | Platform | 2026-04-29 | 11 | 9 | 1 | 1 | 100%
INT-07 | A. Vogel | Platform | 2026-04-30 | 17 | 15 | 2 | 0 | 100%
INT-08 | P. Lang | Platform | 2026-05-02 | 7 | 6 | 0 | 1 | 88%

## Discovery Items
Discovery items — the spine
kind × domain × scope · every item reaches a disposition before lock
Item ID | Kind | Domain | Scope | Finding | Provenance | Confidence | Disposition | Routed to
DI-014 | Pain point | Finance / AP | IT | SdI e-invoices manually rekeyed daily — parent system rejects local VAT codes | INT-04 · 14:31 | High | Accepted | Gap GAP-002
DI-015 | Entanglement | Procurement | GLB | Pricing reads from the parent's shared price master | INT-04 · 14:32 | Medium → verified | Reclassified from pain point | Gap GAP-001
DI-016 | Risk | Treasury | GLB | All payment runs depend on parent treasury — day-one continuity risk | INT-01 · 10:05 | High | Accepted | Gap GAP-006
DI-017 | Decision | Procurement | GLB | Price master ownership after separation | INT-01 · 10:18 | High | Accepted | Open point OP-01
DI-018 | Entanglement | Finance / close | GLB | Month-end close executed inside parent consolidation platform | INT-03 · 09:12 | High | Accepted | Gap GAP-010
DI-019 | Variant | Compliance | IT | SdI / FatturaPA statutory e-invoicing | INT-04 · 14:31 | High | Accepted — justified variant | Variant V-01
DI-020 | Variant | HR / works council | DE | Works-council review on tooling and workflow changes | INT-02 · 09:55 | High | Accepted — justified variant | Variant V-03
DI-021 | Pain point | Procurement | GLB | Approvals above €50k chased by email; no audit trail | INT-05 · 11:40 | High | Accepted | Gap GAP-003
DI-022 | Open question | IT estate | GLB | Which of the 60+ parent-hosted apps are in the separation perimeter? | INT-07 · 15:02 | Low → flagged | Accepted — human verify | Open point OP-03
DI-023 | Process observation | Goods receipt | IT | Paper protocol register at IT plant goods receipt | INT-04 · 14:38 | Medium | Accepted | Gap GAP-013
DI-024 | Risk | Credit | GLB | Credit decisions die with the parent bureau feed at separation | INT-06 · 11:08 | High | Accepted | Gap GAP-007
DI-025 | Insight | SSC | GLB | SSC headcount is 40% allocated to parent work — stranded cost at separation | INT-03 · 09:40 | Medium | Accepted | Value driver: stranded cost

## Open Points
Open points — decisions register
Named owner, due date, blocking status · the lock requires zero blocking
ID | Question | Owner | Raised from | Due | Blocking | Status
OP-01 | Who owns the price master after separation? | K. Maurer · CFO | DI-017 | 2026-05-20 | Yes | Resolved — own master, dual-run 4 wks
OP-02 | TSA duration for AP service centre | K. Maurer · CFO | DI-016 | 2026-05-22 | Yes | Resolved — 9 months
OP-03 | App-by-app disposition of parent-hosted estate | A. Vogel · IT | DI-022 | 2026-06-15 | No | In discussion
OP-04 | Credit bureau contract — own vs broker | L. Conti | DI-024 | 2026-06-10 | No | In discussion
OP-05 | Payroll provider selection DE/IT | HR advisor | INT-02 | 2026-06-30 | No | Open

## Decision Log
Decision log
Every resolved decision carries its rationale and its evidence
Decision | Resolved | Decided by | Rationale | Evidence trail
Own price master; sever parent feed at day one | 2026-05-18 | K. Maurer | TSA pricing exposed margin data to parent; dual-run de-risks cutover | OP-01 ← DI-017 ← INT-01 · 10:18
AP service centre TSA: 9 months | 2026-05-21 | K. Maurer + parent CFO | Own payables build needs 6 months + 2 parallel cycles | OP-02 ← DI-016 ← INT-01 · 10:05
SdI native integration in phase 1 | 2026-05-25 | Steering committee | Statutory; eliminates 2-FTE daily workaround; blocks billing otherwise | GAP-002 ← DI-014 ← INT-04 · 14:31

## Traceability
Traceability sample
Deliverable line → assessment row → discovery item → interview moment
Deliverable line | Assessment row | Discovery item | Interview moment
Requirements R-008 — Own price master, parent feed severed | Entanglement · shared price master — sever before day one | DI-015 · Entanglement | M. Rossi · INT-04 · 14:32 — “…we still read it from the parent's shared price master.”
Requirements R-007 — Standalone VAT code set for IT entity | Fit-gap · SdI e-invoice mapping — replace | DI-014 · Pain point | M. Rossi · INT-04 · 14:31 — “Every SdI e-invoice gets manually rekeyed…”
Exec deck p.6 — Day-one continuity risks | Entanglement · payment runs via parent treasury | DI-016 · Risk | K. Maurer · INT-01 · 10:05 — “If treasury access ends at close, we cannot pay suppliers.”